## Product Backlog
Electric Vehicle Population
Project Name | Electric Vehicle Population
User Story | Plan for a Electric Vehicle Population involves breaking the overal project into 8 manageable phases. With each sprint lasting around 2 weeks. The project will be divided into tasks such as site preparation.
Project Manager | XYZ
Duration | 4 months
Start date | 2025-01-01
End Date | 2025-08-30
Sprint Duration | 2 Weeks Per Sprint
Sprint Goal | this will require concerted strategies across five areas: new product development, go-to-market/distribution, customer segment prioritization, software development, and charging infrastructure.
Budget | 50,00,000/-
Assignee | labour charges (Per Sprint)
Project Manager | 60,000/-
Developer | 10,000/-
Tester | 10,000/-
Data scienctist | 15,000/-
Data analyst | 10,000/-
Total | 1,05,000/-

## Sprint 1
SPRINT 1 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY
| India’s overall EV penetration is expected to grow 8x by 2030, jumping from 5% to 40%+ | Develop “customer-back” products to optimize capital expenditure | Developer | 2024-01-06 | 2024-06-06 | 5 | Complete | High
|  | Reimagine distribution models to grow beyond metro and Tier 1 cities | Tester | 2024-03-06 | 2024-11-06 | 8 | Complete | High
|  | Use software as a differentiator and profitability driver | Data scientist | 2024-03-06 | 13/6/2024 | 10 | Complete | High
|  | Scale charging infrastructure | Data analyst | 2024-04-06 | 2024-08-06 | 5 | Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 50 Lakh | 10,00,000/- | 10,000/- | 35,000/- | 55,000/- | 1,00,000/- | 40,00,000/-

## Sprint 2
SPRINT 2 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY
| Targeted unlocks could propel 2W EV penetration to 45%+ by 2030 | Develop “customer-back” products to optimize capital expenditure | Developer | 15/6/2024 | 20/6/2024 | 5 | Complete | High
|  | Reimagine distribution models to grow beyond metro and Tier 1 cities | Tester | 15/6/2024 | 27/6/2024 | 11 | Complete | High
|  | Use software as a differentiator and profitability driver | Data scientist | 18/6/2024 | 21/6/2024 | 4 | Complete | High
|  | Scale charging infrastructure | Data analyst | 17/6/2024 | 25/6/2024 | 8 | Not Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 50 Lakh | 1,00,000/- | 5,000/- | 30,000/- | 45,000/- | 80,000/- | 8,20,000/-

## sprint 3
SPRINT 3 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 2W EV product unlocks | A mid-segment EV scooter product could enable 50%+ penetration in scooters, a huge jump from 10%–15% penetration | Developer | 29/6/2024 | 2024-12-07 | 12 | Complete | High
|  | Breakthrough motorcycle products could propel motorcycle EV penetration to 30%+ | Tester | 29/6/2024 | 2024-12-07 | 12 | Complete | High
|  | Battery swapping will enable lower-cost offerings | Data scientist | 2024-01-07 | 2024-09-07 | 8 | Complete | Medium
|  | Battery swapping will enable lower-cost offerings | Data analyst | 2024-01-07 | 2024-06-07 | 6 | Complete | Low
|  |  | D 4 |  |  | 2 | Complete | High | Sprint 2
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 1,20,000/- | 10,000/- | 50,000/- | 60,000/- | 1,20,000/- | 7,00,000/-

## Sprint 4
SPRINT 4 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 2W EV GTM unlocks | A mid-segment EV scooter product could enable 50%+ penetration in scooters, a huge jump from 10%–15% penetration | Developer | 2024-12-07 | 18/7/2024 | 6 | Complete | Medium
|  | Breakthrough motorcycle products could propel motorcycle EV penetration to 30%+ | Tester | 15/7/2024 | 23/7/2024 | 8 | Complete | Medium
|  | Battery swapping will enable lower-cost offerings | Data scientist | 2024-12-07 | 23/7/2024 | 10 | Complete | Medium
|  | Battery swapping will enable lower-cost offerings | Data analyst | 15/7/2024 | 18/7/2024 | 4 | Complete | Low
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 90,000/- | 5,000/- | 35,000/- | 50,000/- | 90,000/- | 6,10,000/-

## Sprint 5
SPRINT 5 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 2W EV GTM unlocks | A re-imagined distribution model will be key to driving 2W EV penetration | Developer | 26/7/2024 | 18/7/2024 | 8 | Complete | High
|  | New online channels (e.g., community-led D2C, digital-led lead generation) will also emerge to support 2W EV sales | Tester | 26/7/2024 | 18/7/2024 | 8 | Complete | High
|  | A “scientific” secondary market will be key to drive EV penetration in India | Data scientist | 26/7/2024 | 31/7/2024 | 5 | Not Complete | Medium
|  | Inspect electrical Systems | Data analyst |  |  |  | Not Started | Low
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 1,00,000/- | 10,000/- | 30,000/- | 60,000/- | 1,00,000/- | 5,10,000/-

## Sprint 6
SPRINT 6 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 2W EV manufacturing unlocks | A localized supply chain and India-specific component innovation would significantly accelerate EV penetration | Developer | 2024-09-08 | 20/8/2024 | 9 | Complete | High
|  | In 3W cargo, introduction of an entry-level EV model will be key to propel EV adoption | Tester | 2024-09-08 | 22/7/2024 | 11 | Complete | High
|  | OEMs need to strengthen their B2B-specific GTM capabilities and deepen engagement with B2B customers to accelerate EV penetration | Data scientist | 2024-09-07 | 2024-10-07 | 8 | Complete | Medium
|  | Offline dealer networks are critical for 3W EVs to take off, due to the prevalence of consultation-based sales | Data analyst | 2024-09-08 | 20/8/2024 | 9 | Complete | High
|  | OEMs need to develop 3W passenger EVs matching compressed natural gas (CNG) counterparts | D 3 |  |  | 4 | Complete | Medium | Sprint 5
|  | sustained policy support | D 4 |  |  | 1 | Complete | Low | Sprint 5
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 1,30,000/- | 15,000/- | 45,000/- | 70,000/- | 1,30,000/- | 3,80,000/-

## Sprint 7
SPRINT 7 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 3W EV Market | A localized supply chain and India-specific component innovation would significantly accelerate EV penetration | Developer | 23/8/2024 | 2024-03-09 | 10 | Complete | High
|  | In 3W cargo, introduction of an entry-level EV model will be key to propel EV adoption | Tester | 26/8/2024 | 31/7/2024 | 6 | Complete | High
|  | OEMs need to strengthen their B2B-specific GTM capabilities and deepen engagement with B2B customers to accelerate EV penetration | Data scientist | 23/8/2024 | 2024-02-09 | 9 | Complete | Medium
|  | Offline dealer networks are critical for 3W EVs to take off, due to the prevalence of consultation-based sales | Data analyst | 23/8/2024 |  | 12 | Not Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 80,000/- | 5,000/- | 25,000/- | 50,000/- | 80,000/- | 3,00,000/-

## Sprint 8
SPRINT 8 :
| USER STORY | TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| 3W EV Market | A localized supply chain and India-specific component innovation would significantly accelerate EV penetration | Developer | 2024-06-09 | 2024-11-09 | 5 | Complete | Medium
|  | In 3W cargo, introduction of an entry-level EV model will be key to propel EV adoption | Tester | 2024-06-09 | 2024-11-09 | 5 | Complete | Medium
|  | OEMs need to strengthen their B2B-specific GTM capabilities and deepen engagement with B2B customers to accelerate EV penetration | Data scientist | 2024-09-09 | 17/9/2024 | 8 | Complete | Medium
|  | Offline dealer networks are critical for 3W EVs to take off, due to the prevalence of consultation-based sales | Data analyst | 18/9/2024 | 21/9/2024 | 4 | Complete | High
|  | OEMs need to develop 3W passenger EVs matching compressed natural gas (CNG) counterparts | D 4 |  |  |  | Complete | High | Sprint 7
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 10 Lakh | 1,40,000/- | 20,000/- | 50,000/- | 70,000/- | 1,40,000/- | 2,40,000/-